## Initial Plan
Color Coding |  | Completed |  |  |  | SPRING 2022 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[5 empty] | Date | 2022-01-25 | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-07 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals | ALL | 2022-01-10 | 2022-01-23 | 100%
| Confirm Project Team Roles | ALL | 2022-01-05 | 2022-01-11 | 100%
| Develop two business cases | Avni Mitawalkar | 2022-01-30 | 2022-02-09 | 100%
| Develop Project Initiation Document (PID) | All | 2022-02-11 | 2022-02-14 | 100%
| Produce initial Project Plan, RACI | All | 2022-02-17 | 2022-02-18 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles | Avni Mitawalkar | 2022-02-23 | 2022-03-03 | 100%
| Produce Context Diagram, Define System Interfaces | Sen Wang | 2022-02-23 | 2022-03-03 | 100%
| Collect Customer Needs | All | 2022-02-23 | 2022-03-01 | 100%
| Define Business Requirements | Avni Mitawalkar | 2022-03-01 | 2022-03-06 | 100%
| Agree to System Requirements types | All | 2022-03-01 | 2022-03-02 | 100%
| Define Functional Decomposition | All | 2022-03-01 | 2022-03-06 | 100%
| Produce RCT document | Sen Wang | 2022-03-01 | 2022-03-07 | 100%
| Decide which features to implement this semester | All | 2022-03-10 | 2022-03-22 | 100%
| Produce analysis diagrams (UML, DFD) | Sen Wang | 2022-03-10 | 2022-03-22 | 100%
| Define functional requirements (User Stories) | Sen Wang | 2022-03-10 | 2022-03-22 | 100%
| Update Project Plan with additional requirements tasks | Daksh Rawat | 2022-03-01 | 2022-03-22 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (Logical View) | Nikita Jarile, Manoj Srinivasu | 2022-03-22 | 2022-04-10 | 100%
| Architecture design (Process View) | Nikita Jarile, Manoj Srinivasu | 2022-03-22 | 2022-04-10 | 100%
| GitHub Repository | Daksh Rawat | 2022-03-22 | 2022-04-10 | 100%
| Database Design (ERD, Table spec) | Manoj Srinivasu | 2022-03-22 | 2022-04-04 | 100%
| System Interface Design | Nikita Jarile, Sanket Koli | 2022-04-15 | 2022-04-19 | 0%
| User interface design | Nikita Jarile, Sanket Koli | 2022-04-15 | 2022-04-19 | 0%
| Class Diagram (UML) | Nikita Jarile | 2022-04-15 | 2022-04-18 | 100%
| Sequence Diagram (UML) | Nikita Jarile | 2022-04-15 | 2022-04-19 | 100%
| Populate test data in the database tables | Manoj Srinivasu | 2022-04-15 | 2022-04-18 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | GUI & Functionality Detailed Design | Nikita Jarile | 2022-04-05 | 2022-04-19 | 100%
| Establish code repository in GitHUb | Nikita Jarile | 2022-04-05 | 2022-04-19 | 100%
| Coding & Implemenation | Sanket Koli | 2022-04-05 | 2022-04-19 | 100%
Feature Breakdown
01.01 Account Management
| Validate login for Service Providers and Users | Nikita Jarile, Sanket Koli | 2022-04-12 | 2022-04-19 | 100%
01.01 Account Management
| Adding the new restaurants | Nikita Jarile, Sanket Koli | 2022-04-12 | 2022-04-19 | 100%
01.03 User Support
| Form that user provides | Nikita Jarile, Sanket Koli | 2022-04-12 | 2022-04-19 | 100%
02.01 Searching for Restaurants
| Search restaurants for orders placeing | Nikita Jarile, Sanket Koli | 2022-04-12 | 2022-04-19 | 100%
02.02 Searching For Food Items
| Search food for orders placing | Nikita Jarile, Sanket Koli | 2022-04-12 | 2022-04-19 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document | Divya Kotapati | 2022-04-15 | 2022-04-25 | 100%
| Evaluate Features to be Tested | Divya Kotapati | 2022-04-15 | 2022-04-26 | 100%
| 01.01 Account Management | Divya Kotapati | 2022-04-15 | 2022-04-26 | 100%
User Registeration:- (Test whether a user can register/create account)
User Login:- (Test whether a user can login once they have registered)
| 01.03 User Support | Divya Kotapati | 2022-04-15 | 2022-04-25 | 100%
I Have Input:- (To test whether the user is successfully able to input their feedback that they have)
| 02.01 Searching for Restaurants | Divya Kotapati | 2022-04-15 | 2022-04-25 | 100%
Find Restaurant:- (To test whether the user is successfully able to search the restaurant by the input that they give as name of restaurant)
| 02.02 Searching For Food Items | Divya Kotapati | 2022-04-15 | 2022-04-25 | 100%
Find food items:- (To test whether the user is successfully able to search the food items by the input that they give as the name of food item)
| Design Test Cases | Divya Kotapati | 2022-04-15 | 2022-04-26 | 100%
| Execute Test Cases | Divya Kotapati | 2022-04-22 | 2022-04-29 | 100%
| Anaylze Test Results | Divya Kotapati | 2022-04-29 | 2022-05-06 | 100%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2022-05-06 | 2022-05-10 | 75%