## RACI
Project Roles
Project Phase | Project Tasks | Project Manager | Product Owner | Lead Dev | Developer | Lead BA | Tester | DBA
Project Management | Develop a project plan | A,R | C | C | I | C | I | I
| Provide cost estimate | A,R | C | I | I | C | I | I
| Hire resources | A,R | C | R | I | I | I | C
| Establish a project documentation portal | A,R | I | C | C | I | I | I
| Maintain a project risk and issue log | A,R | I | C | C | C | I | C
| Provide project status reports | A | I | R | C | I | I | I
Requirements | Perform requirements analysts | A | C | C | C | R | C | I
| Gather business requirements | A | R | I | C | R | I | I
| Produce functional requirements | A | C | C | C | R | I | I
Design | Produce high-level design specs | A | I | R | C | I | I | C
| Produce data model | A | I | R | I | I | I | R
| Produce detailed design specs | A | I | R | I | I | I | C
Coding | Establish a code repository (GitHub) | A | I | R | R | C | I | C
| Develop component code | A | I | R | R | I | I | I
Testing | Develop a test plan | A | C | C | C | C | I | C
| Establish a test repository | A | I | C | C | I | I | C
| Develop test specifications | A | I | I | C | I | R | I
| Execute testing, report defects | A | C | I | C | C | R | I
| Conduct defect review calls | A | C | C | C | I | C | I
| Produce, deliver defect metrics | A | C | C | I | I | R | I
| Support test environments | A | I | R | C | I | C | R
Deployment | Produce a deployment plan | A | I | R | I | I | I | R
| Produce deployment procedures | A | I | R | I | I | I | R
| Deploy software into production | A | I | R | I | I | I | R